## Overview
Python Q&A Chatbot: 5-Day Tracker
Tick tasks on the 'Tasks' sheet (yellow Done column, pick ☑ from the dropdown). This sheet updates automatically.
Day | Date | Focus | Planned hrs | Tasks done | Total tasks | Hours done | Progress | Status
1 | 2026-10-13 | Setup and understanding | 3.25 | 0 | 5 | 0 | 0% | Not started
2 | 2026-10-14 | Knowledge base, part 1 | 4 | 0 | 6 | 0 | 0% | Not started
3 | 2026-10-15 | Knowledge base, part 2 and testing | 4.25 | 0 | 6 | 0 | 0% | Not started
4 | 2026-10-16 | Improvements and tuning | 4.5 | 0 | 6 | 0 | 0% | Not started
5 | 2026-10-17 | Polish and submit | 3 | 0 | 7 | 0 | 0% | Not started
Total |  |  | 19 | 0 | 30 | 0 | 0% | Not started
Overall progress |  | 0%
Days completed |  | 0 of 5
Note: Planned hours are the sum of task minutes on the Tasks sheet (about 19 hrs; the earlier plan rounded to 18).

## Tasks
Day | Date | Task | Time (min) | Done
1 | 2026-10-13 | Install Python, create venv, run pip install -r requirements.txt | 30 | ☐
1 | 2026-10-13 | Run chatbot.py and streamlit run app.py, test 15-20 questions | 30 | ☐
1 | 2026-10-13 | Read chatbot.py line by line and write notes on each method | 60 | ☐
1 | 2026-10-13 | Learn TF-IDF, cosine similarity and the threshold idea | 60 | ☐
1 | 2026-10-13 | Create the GitHub repo and make the first commit | 15 | ☐
2 | 2026-10-14 | Add 10 Q&As on strings and lists | 50 | ☐
2 | 2026-10-14 | Add 10 Q&As on dicts, sets and tuples | 50 | ☐
2 | 2026-10-14 | Add 10 Q&As on loops, conditionals and functions | 50 | ☐
2 | 2026-10-14 | Test each new entry with 2 differently worded questions | 60 | ☐
2 | 2026-10-14 | Fix entries that matched wrongly (improve keywords) | 15 | ☐
2 | 2026-10-14 | Commit and push (target: about 65 entries) | 15 | ☐
3 | 2026-10-15 | Add 10 Q&As on OOP and exceptions | 50 | ☐
3 | 2026-10-15 | Add 10 Q&As on file handling and modules | 50 | ☐
3 | 2026-10-15 | Add 10 Q&As on NumPy, pandas and interview questions | 50 | ☐
3 | 2026-10-15 | Write test_bot.py with (question, expected match) pairs | 60 | ☐
3 | 2026-10-15 | Print pass/fail and an accuracy percentage | 30 | ☐
3 | 2026-10-15 | Commit and push (target: about 95 entries) | 15 | ☐
4 | 2026-10-16 | Test thresholds 0.15, 0.2 and 0.3, then pick the best | 60 | ☐
4 | 2026-10-16 | Handle empty input, 'thanks' and 'bye' | 45 | ☐
4 | 2026-10-16 | Add 'Did you mean...?' showing top 3 matches on low confidence | 90 | ☐
4 | 2026-10-16 | Load the JSON into pandas and check duplicates and missing fields | 45 | ☐
4 | 2026-10-16 | Re-run tests and note the new accuracy | 15 | ☐
4 | 2026-10-16 | Commit and push | 15 | ☐
5 | 2026-10-17 | Tidy the Streamlit UI | 30 | ☐
5 | 2026-10-17 | Take 3-4 screenshots | 15 | ☐
5 | 2026-10-17 | Finalize the README (overview, how it works, setup, screenshots, accuracy) | 60 | ☐
5 | 2026-10-17 | Clean the code with comments and consistent naming | 30 | ☐
5 | 2026-10-17 | Push the final version and make the repo public | 15 | ☐
5 | 2026-10-17 | Prepare answers to likely mentor questions | 20 | ☐
5 | 2026-10-17 | Add the project to your resume | 10 | ☐

## Habits
Daily habit | Done today?
Commit to GitHub every day | ☐
Study in focused blocks of 50 min with 10 min breaks | ☐
From Oct 18, spend 20-30 min a day collecting face images | ☐
Reset the checkboxes to ☐ each morning. Yellow cells are the ones you edit.